## Charter
PROJECT CHARTER
Simulated project for portfolio purposes, based on Oracle database operations experience. All figures are illustrative assumptions.
Project Title | Oracle 21c Database Migration & Upgrade Program
Objective | Migrate the company's production Oracle databases from legacy on-premise servers to a new Oracle 21c environment with zero data loss and less than 4 hours of planned downtime.
In Scope | Assessment of 12 databases, new server setup, data migration, backup and recovery configuration, user access migration, testing, go-live, and handover.
Out of Scope | Application code changes, hardware procurement, and end-user training.
Key Deliverables | Assessment report, migration plan, configured 21c environment, tested backup/recovery, UAT sign-off, go-live, and a handover document.
Project Start Date | 2026-11-02
Project End Date | 2027-01-22
Duration (weeks) | 12
Budget (INR) | 2500000
Overall % Complete | 0%
Success Criteria | No data loss; downtime under 4 hours; delivered within 5% of budget; UAT passed with zero critical defects.
Key Risks | Data corruption during migration, downtime overrun, resource unavailability, compatibility issues.
STAKEHOLDERS
Role | Responsibility
Sponsor | Approves budget and scope
Project Manager | Plans, tracks, and reports
DBA Lead | Technical migration
Application Owner | UAT and sign-off
Infrastructure Team | Servers and network
LEGEND & ASSUMPTIONS
Blue text on yellow | Input cells you can edit: Project Start Date, Budget, and on the WBS_Schedule sheet the Duration, Depends On and % Complete columns. Everything else recalculates automatically.
Green text | Values pulled from another sheet.
Assumption | Durations are in working days (Mon-Fri); weekends are skipped and public holidays are not modelled.
Assumption | Budget (INR 25,00,000), timeline and scope are illustrative assumptions for this simulated project.
Assumption | Tasks run one after another, so every task is on the critical path: any delay moves the Go-live date.

## WBS_Schedule
WORK BREAKDOWN STRUCTURE & SCHEDULE
Edit the blue cells (Duration, Depends On, % Complete). Start and End dates calculate automatically from the dependency chain and the project start date on the Charter sheet.
ID | Task | Phase | Owner | Start | End | Duration (working days) | Depends On | % Complete | Milestone | Critical Path
1.1 | Kickoff and charter approval | Planning | Project Manager | 2026-11-02 | 2026-11-03 | 2 | - | 0% |  | Yes
1.2 | Assess current databases | Planning | DBA Lead | 2026-11-04 | 2026-11-10 | 5 | 1.1 | 0% |  | Yes
1.3 | Prepare migration plan | Planning | DBA Lead | 2026-11-11 | 2026-11-16 | 4 | 1.2 | 0% | Plan approved | Yes
2.1 | Set up new servers | Setup | Infrastructure Team | 2026-11-17 | 2026-11-23 | 5 | 1.3 | 0% |  | Yes
2.2 | Install Oracle 21c | Setup | DBA Lead | 2026-11-24 | 2026-11-26 | 3 | 2.1 | 0% |  | Yes
2.3 | Configure backup and recovery | Setup | DBA Lead | 2026-11-27 | 2026-12-02 | 4 | 2.2 | 0% | Environment ready | Yes
3.1 | Migrate test database | Migration | DBA Lead | 2026-12-03 | 2026-12-09 | 5 | 2.3 | 0% |  | Yes
3.2 | Validate data integrity | Migration | DBA Lead | 2026-12-10 | 2026-12-15 | 4 | 3.1 | 0% |  | Yes
3.3 | Migrate user access and roles | Migration | DBA Lead | 2026-12-16 | 2026-12-18 | 3 | 3.2 | 0% |  | Yes
4.1 | Performance testing | Testing | DBA Lead | 2026-12-21 | 2026-12-25 | 5 | 3.3 | 0% |  | Yes
4.2 | User acceptance testing (UAT) | Testing | Application Owner | 2026-12-28 | 2027-01-01 | 5 | 4.1 | 0% |  | Yes
4.3 | Fix defects and retest | Testing | DBA Lead | 2027-01-04 | 2027-01-07 | 4 | 4.2 | 0% | UAT sign-off | Yes
5.1 | Go-live cutover | Go-Live | DBA Lead | 2027-01-08 | 2027-01-11 | 2 | 4.3 | 0% | Go-live | Yes
5.2 | Post go-live monitoring | Go-Live | DBA Lead | 2027-01-12 | 2027-01-15 | 4 | 5.1 | 0% |  | Yes
6.1 | Handover and documentation | Handover | DBA Lead | 2027-01-18 | 2027-01-20 | 3 | 5.2 | 0% |  | Yes
6.2 | Project closure and lessons learned | Handover | Project Manager | 2027-01-21 | 2027-01-22 | 2 | 6.1 | 0% | Project closed | Yes
| Total working days / project span |  |  | 2026-11-02 | 2027-01-22 | 60
Critical Path = 'Yes' for all tasks because each task depends on the one before it (assumption).
Formulas:
Start = WORKDAY(INDEX(F5:F20,MATCH([Depends On],A5:A20,0)),1)
End = WORKDAY([Start],[Duration (working days)]-1)

## Gantt
GANTT CHART: Oracle 21c Database Migration & Upgrade Program
Chart updates automatically from the WBS_Schedule sheet. Columns are weeks (week-start date shown). Diamond = milestone.
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
ID | Task | Phase | Start | End | Milestone | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01
1.1 | Kickoff and charter approval | Planning | 2026-11-02 | 2026-11-03
1.2 | Assess current databases | Planning | 2026-11-04 | 2026-11-10
1.3 | Prepare migration plan | Planning | 2026-11-11 | 2026-11-16 | Plan approved | bar: 2026-11-16
2.1 | Set up new servers | Setup | 2026-11-17 | 2026-11-23
2.2 | Install Oracle 21c | Setup | 2026-11-24 | 2026-11-26
2.3 | Configure backup and recovery | Setup | 2026-11-27 | 2026-12-02 | Environment ready | bar: 2026-11-30
3.1 | Migrate test database | Migration | 2026-12-03 | 2026-12-09
3.2 | Validate data integrity | Migration | 2026-12-10 | 2026-12-15
3.3 | Migrate user access and roles | Migration | 2026-12-16 | 2026-12-18
4.1 | Performance testing | Testing | 2026-12-21 | 2026-12-25
4.2 | User acceptance testing (UAT) | Testing | 2026-12-28 | 2027-01-01
4.3 | Fix defects and retest | Testing | 2027-01-04 | 2027-01-07 | UAT sign-off | bar: 2027-01-04
5.1 | Go-live cutover | Go-Live | 2027-01-08 | 2027-01-11 | Go-live | bar: 2027-01-11
5.2 | Post go-live monitoring | Go-Live | 2027-01-12 | 2027-01-15
6.1 | Handover and documentation | Handover | 2027-01-18 | 2027-01-20
6.2 | Project closure and lessons learned | Handover | 2027-01-21 | 2027-01-22 | Project closed | bar: 2027-01-18
Legend (phase colours)
Planning
Setup
Migration
Testing
Go-Live
Handover
◆ Milestone

## Milestones
MILESTONE TRACKER
A milestone is reached when its linked task finishes. Change the Linked Task ID (blue) to move a milestone.
Milestone | Linked Task ID | Linked Task | Target Date | Status
Plan approved | 1.3 | Prepare migration plan | 2026-11-16 | Pending
Environment ready | 2.3 | Configure backup and recovery | 2026-12-02 | Pending
UAT sign-off | 4.3 | Fix defects and retest | 2027-01-07 | Pending
Go-live | 5.1 | Go-live cutover | 2027-01-11 | Pending
Project closed | 6.2 | Project closure and lessons learned | 2027-01-22 | Pending
Formulas:
Target Date = INDEX(WBS_Schedule!$F5:F20,MATCH([Linked Task ID],WBS_Schedule!$A5:A20,0))